## Sheet1
Work Log | [6 empty] | Status values: | Priority values
Category | Work Item | Status | Cost (hrs) | Start Date | End Date | Partner | Active | 1
Brainstorming | Finding a project to do | Done | 2 | 2023-05-16 | 2023-05-18 | Both | Cut | 2
Project Charter | Writing the doc | Done | 2 | 2023-05-19 | 2023-05-21 | Both | Done | 3
Planning | Figuring out who will code which part | Done | 1 | 2023-05-21 | 2023-05-21 | Both
Revewing | Reviewing Powerpoints from pervious semesters to find info on logistics | Done | 1 | 2023-05-22 | 2023-05-24 | Both
adding words to a database | Research | Done | 0.5 | 2023-05-23 | 2023-05-23 | Rohan
PsuedoCode | Going over the general plan and ideas | Done | 1 | 2023-05-24 | 2023-05-25 | Both
Starting Code on Intellij | creating classes, adding comments, pushing to git | Done | 1 | 2023-05-26 | 2023-05-26 | Meymey
UI | Research on UI Javaswing | Cut | 1 | 2023-05-30 | 2023-05-30 | Rohan
Debugging | Having users test the program and look for errors | Done | 2 | 2023-05-30 | 2023-06-04 | Rohan
Adding another word | editing code | Done | 2 | 2023-06-04 | 2023-06-04 | Meymey
Reviewing project Charter | writing in doc | Done | 1 | 2023-06-04 | 2023-06-04 | Both
Submit!! | Submit!! | Done | 0 | 2023-06-05 | 2023-06-05 | Both